Zanbeel Version Control — Capability Gap Analysis and Delivery Roadmap

Prepared for engineering management  ·  Four-week delivery plan  ·  Scope: 32 capabilities across 5 areas

1.  Why this work is needed

Zanbeel is the version control system holding the organisation's source code — 63 repositories and 37,466 tracked files. It was audited line by line against the capabilities a team expects from a standard version control system (Git, GitHub, GitLab). The audit was evidence-based: every finding was reproduced against the running server, the production database, the web client and the fox CLI.

The review found 32 capability gaps. Several are not conveniences but risks to the integrity and availability of the code itself: pushes were accepted without authentication, 92% of the 4.2 GB database was build artefacts rather than source, and the only backup was a single stale 520 KB file with no restore path anyone had ever run.

2.  Where Zanbeel differs from a standard VCS

| Area | Risk | What is missing today |
| --- | --- | --- |
| Core version control | Critical | No ignore-file support or push size limits, so build artefacts and archives entered the object store unchecked. No compression or external object storage, no garbage collection, no line-level blame, no rebase / cherry-pick / revert, and no commit signing — history could be altered in the database undetectably. |
| Review and collaboration | Critical | No approval gate on merges. A conflicted merge reported the conflict and stopped, with no way to resolve it. Branch protection existed as unused code. No inline diff comments, no code owners, and contributing required granting outsiders write access. |
| Automation and integration | High | The CLI authenticated by sending the user's actual password, so a compromised machine meant a password rotation. No webhooks, so every integration would have to poll. Nothing could report build status against a commit or block a merge on it. No server-side push policy. No key-based authentication. |
| Discovery and navigation | High | Only issues were searchable — no way to find a string across a repository's files or locate a commit by message. Roughly 44% of the API had no user interface: activity, notifications, tags, releases, branch management and generated documentation were reachable only from the CLI. |
| Security and operations | High | The login endpoint had no attempt counter, delay or lockout. No tested backup or restore procedure. Schema changes were ad-hoc statements that printed a warning and continued on failure, leaving the server running against a schema it believed it had applied. List endpoints returned everything and grew without bound. |

3.  Delivery approach

The work is sequenced so that each week ends with a demonstrable, independently useful increment rather than a single delivery at the end of the month. Foundations come first: there is no value in review workflow or integrations built on an object store that is still accepting 900 MB archives. Each week closes with a checkpoint — the increment is verified against production-scale data, reviewed, and signed off before the next begins.

4.  Four-week schedule

| Workstream | Deliverable | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- | --- |
|  |  | Days 1–5 | Days 6–10 | Days 11–15 | Days 16–20 |
| Audit and baseline | Full codebase review; modularise the 6,461-line server file; establish test baseline |  |  |  |  |
| Object store and push policy | Ignore rules, push size limits, compression, external blob storage, garbage collection |  |  |  |  |
| History integrity | Line-level blame; rebase, cherry-pick and revert; commit signing and verification |  |  |  |  |
| Review workflow | Approval gate, inline diff comments, code owners, fork and contribute upstream |  |  |  |  |
| Merge conflict resolution | Server-side resolution sessions; branch protection enforced on push and merge |  |  |  |  |
| Credentials | Scoped revocable access tokens; SSH public-key authentication |  |  |  |  |
| Integrations | Signed webhooks with delivery log; CI status checks as a merge gate; push rules |  |  |  |  |
| Discovery and navigation | Repository, commit and code search; activity audit view; notification surface |  |  |  |  |
| Repository management UI | Branch operations, tags and releases, generated documentation in the web client |  |  |  |  |
| Security and operations | Login rate limiting; verified backup and restore; schema migrations; pagination |  |  |  |  |
| Verification and rollout | Production-scale verification, staged deployment and sign-off — continuous |  |  |  |  |

Solid bar = focused delivery week.   Light bar = continuous activity across the month.

5.  Weekly checkpoints

| Checkpoint | What management will be able to see |
| --- | --- |
| End of week 1 | Object store under control. Artefacts no longer enter the repository; storage footprint reduced and reclaimable space reported. |
| End of week 2 | History is trustworthy. Every commit is attributable and tamper-evident; blame and history rewriting operations available. |
| End of week 3 | Code review and automation in place. Merges are gated on approval and build status; machines authenticate with scoped credentials rather than passwords. |
| End of week 4 | The platform is operable. Everything the API offers is reachable from the interface, sign-in is protected, and a backup has been taken and restored as a test. |

6.  Explicitly outside this month

Four items are deliberately deferred so the month is deliverable rather than optimistic. Two-factor authentication is a separate piece of work with its own enrolment and recovery design. Stash and submodules are convenience features with no integrity or availability impact. The migration from SQLite to PostgreSQL has five prerequisites of its own — including moving file contents out of the database, which this month's storage work makes possible — and is proposed as the following cycle.

Scope, sequencing and risk ratings derive from a full audit of the backend, the React client, the fox CLI and read-only queries against the production database. Severity reflects impact on a team relying on Zanbeel as their version control system, not implementation effort.